## Sheet1
Start of Block | End of Block | Block Length | Notes | Work to be Done | Milestones
2022-10-14 | 2022-10-21 | 7 |  | Research - how to implement Epidemic protocol, evaluation methods used for ad-hoc networks | Develop a greater understanding of the Epidemic protocol and a plan for implementing it, create an evaluation plan | dual core - have threading - research threads in circuit and micropython -- how to get | Dates do not include the start of block date but do include the end of block date
2022-10-21 | 2022-10-28 | 7 |  | Learning how to use the microcontroller and boards | Ensure all the necessary hardware is available, develop a greater understanding of the Raspberry Pi Pico and CircuitPython
2022-10-28 | 2022-11-04 | 7 |  | Start to work with the hardware - implement point to point communication between two nodes | Two nodes can send point to point messages
2022-11-04 | 2022-11-18 | 14 | 07/11 - Robotics Assignment 1 | Implement controlled flood routing | Messages are flooded between at least three nodes
2022-11-18 | 2022-12-02 | 14 | 19/11 - 4s head; 28/11 - Robotics Assignment 2 | Implement Epidemic routing protocol | Routing state information is shared between at least two nodes, Epidemic is implemented
2022-12-02 | 2022-12-10 | 8 |  | Test, tweak and debug Epidemic implementation on hardware | Epidemic is implemented on hardware | If time, just work on the damn application layer
2022-12-10 | 2022-12-26 | 16 | 14/11 - Trial 8s; Christmas | Time off | -
2022-12-26 | 2023-01-02 | 7 | 01/01 -> 11/01 - Camp | Implementing application layer - read location data from GPS and warn user when approaching known obstacle | The device warns the user when they are approaching a known obstacle
2023-01-02 | 2023-01-16 | 14 | 01/01 -> 11/01 - Camp | Implementing application layer - transfer data between the application and routing layers | The application layer is implemented on hardware
2023-01-16 | 2023-01-23 | 7 |  | Tweaking the hardware, testing point to point links on land | The hardware runs on land, finish proof of concept
2023-01-23 | 2023-01-30 | 7 |  | Water testing and tweaking | The hardware is implemented and run in the application environment (water)
2023-01-30 | 2023-02-03 | 4 | 03/02 - Cybercrime 1 | Write progress report and presentation | Progress report and presentation | How to evaluate - ITU is super irrelevant bc of the topology
2023-02-03 |  |  | Progress report and presentation
2023-02-03 | 2023-02-14 | 11 |  | Evaluation and tweaking on land | The hardware is evaluated for correctness on land
2023-02-14 | 2023-02-21 | 7 | 17/02 - Cybercrime 2 | Evaluation and tweaking on water | The hardware is evaluated for performance on water
2023-02-21 | 2023-03-07 | 14 | 03/03 - Cybercrime 3 | Dissertation - plan and bullet point what will be said | Dissertation bullet point form (first draft)
2023-03-07 | 2023-03-21 | 14 | 17/03 - Cybercrime 4 | Dissertation - write out preparation and implementation | Dissertation has implementation and preparation written out
2023-03-21 | 2023-04-04 | 14 | 26/03 - The Boat Race | Time off | -
2023-04-04 | 2023-04-18 | 14 |  | Dissertation - write introduction, conclusion, evaluation | Dissertation fully written, sent to supervisor to proofread (second draft)
2023-04-18 | 2023-05-02 | 14 |  | Dissertation - Take on criticism, add references and appendices | Dissertation - final draft
2023-05-02 | 2023-05-12 | 10 |  | Contingency | -
2023-05-12 |  |  | Final deadline